## Sheet1
Summary | Markets | Description
[VF7NP] [Air Tightness] VF7NP concerned airleakage position in exterior summary | VN - Viet Nam | Baseline (no taping anything) result: 248l/s Standard result VF7NP: 47l/s observed position in exterior: 1.Right and left door fixed glass 2.Missing license plate lamp, cover for tailgate switch 3.Bumper bracket 4.Rear camera 5.Tailgate lock 6. Rear lamp
[VF7 NP] [FRS 7C.1.2.2 v5] [Network]: VehicleControl: CVC send Method ID 0x901c and 0x102a (Wiper_ServiceMode_Ready) wrong value at Precondition (Vehicle_Operation_State=0x1) | VN - Viet Nam | Step: 1. Record log CAN and ETH 2. Change the Vehicle_Operation_State = 0x0/0x1/0x2/0x3 3. Check the Precondition of all ETH msg Expected Result: ● When Vehicle_Operation_State = 0x1, Payload of 0x901c and 0x102a = 01 (Service ID 0x2022) Actual Result: ● When Vehicle_Operation_State = 0x2/0x3, Payload of 0x901c and 0x102a = 01 ● When Vehicle_Operation_State = 0x1, Payload of 0x901c and 0x102a = 00 Impact: ● Can not turn on Wiper Service Mode when Vehicle Operation State at ACC.
The result of the air tightness test does not meet the SSTS objective | VN - Viet Nam | After the EP-13 complete vehicle airtightness test was completed, a total of 14 leakage points were found. Before sealing, the actual air volume was 194.9 L/S, which did not meet the SSTS target value (≤ 47 L/S). After sealing, the actual air volume was 52.9 L/S. There are 4 leakage points in the opening and closing parts.
The result of the air tightness test does not meet the SSTS objective | VN - Viet Nam | After the EP-13 complete vehicle airtightness test was completed, a total of 14 leakage points were found. Before sealing, the actual air volume was 194.9 L/S, which did not meet the SSTS target value (≤ 47 L/S). After sealing, the actual air volume was 52.9 L/S. There are 3 leakage points in the exterior decoration.
coarse road 80km/h Driver`s Inner Ear SPL not meet VTS requirements | VN - Viet Nam | Test results for Driver`s Inner Ear SPL at 80 km/h on coarse road :75.73 dB, VTS requirement: ＜69 dB. Test results do not meet VTS standards.
coarse road 80km/h Driver`s Inner Ear AI not meet VTS requirements | VN - Viet Nam | Test results for Driver`s Inner Ear AI at 80 km/h on coarse road: 76.54(AI%), VTS requirement:＞ 80 (AI%). Test results do not meet VTS standards.
coarse road 80km/h Steering Wheel Vibration not meet VTS requirements | VN - Viet Nam | Test results for Steering Wheel Vibration at 80 km/h on coarse road: 4.53 m/s2, VTS requirement: ＜2.0m/s2. Test results do not meet VTS standards.
coarse road 80km/h Seat Track Vibration not meet VTS requirements | VN - Viet Nam | Test results for Steering Wheel Vibration at 80 km/h on coarse road: 0.51 m/s2, VTS requirement: ＜0.5m/s2. Test results do not meet VTS standards.
[ePT]VF7(NP)_The value of CVC_BrakeRegenmode is not matched with MHU_BrakeRegenmode | VN - Viet Nam | Test Condition: 1. Vehilce is fully updated to target SW baseline. 2. No error/fail message on MHU screen and vehicle. 3. Vehilce speed <3kmph Test Steps: 1. Vehilce in ON model 2. Press brake and Change Gear P ->D 3. Change Regen config on MHU from OFF <> LOW <> High <-> MID 5. Press brake and Change Gear D ->P Expected Result: Regen function and drive normally No error/fail observe on MHU and vehicle No observe lost HV, Drv system fault Actual Result: The value of CVC_BrakeRegenmode is not matched with MHU_BrakeRegenmode: MHU_BrakeRegenmode always remains at High Recovery: - Occurrences: Always
[ePT]VF7(NP)_Torque descreases unusually when the vehicle gains the max speed | VN - Viet Nam | Test Condition: 1. Vehilce is fully updated to target SW baseline. 2. No error/fail message on MHU screen and vehicle. Test Steps: 1. VehicleMode= ON ( Gear P) 2. Change P to D with Press Brake 3. Press acc Pedal slowly 0~100% to increse Vehilce speed ~ 140Kmph Expected Result: The ACC function and drive normally No error/fail observe on MHU and vehicle No observe lost HV, Drv system fault Actual Result: At t=295s In Step 3, when the driver accelerates and maintains the vehicle at the maximum speed of 140 km/h for 20 seconds, both the motor torque and the target torque decrease unexpectedly, causing the vehicle speed to drop to 130 km/h. Recovery: - Occurrences: 3/5
[Thermal AT&V_VF7NP_EP ] The vehicle does not meet the Cooling performance VTS target under ambient 42 °C | VN - Viet Nam | [Pre-condition] Vehicle Model: VF7NP LHD VN ● Build vehicle : EP2 ● VIN: RLLV3F5CXSL100214 ● Software Version: LTM-134496 ● Test Standard :[^Thermal 001 AC Pull Down 2025 07 03 rev11.pdf] [Step] ● Perform soaking and testing according to the standard: [^Thermal 001 AC Pull Down 2025 07 03 rev11.pdf] [Expect result] ● The cabin temperature meet all the VTS target. ● No warning/ fault / trigger fault during the test [Actual result] ● The cabin temperature did not meet all the VTS target. ● The A/C cooling showed a terrible performance, especially when the chiller was activated ● The BMS chiller threshold is not proper for hot ambient when it is deactivated when BMS max cell temp reaches 27oC.That leads to uncomfortable cabin temperature
[Dynamic]VF7(NP)_Positive packcur is observed (Regen active) when the vehicle roll back on the slope with gear R | VN - Viet Nam | Test Condition: 1. Vehicle stationary, HV ready state 2. No fault in system 3. Door and seatbelt closed 4. Drive mode: SPORT/NORMAL/ECO 5. Creep mode: ON 6. Vehicle with full load (if possible) Test Steps: 1. Change gears to R 2. Park the vehicle at the bottom of slope (downhill condition, as high gradient as possible) with gear R 3. Fully press Acc Pedal until the car reaches the top of the slope, fully press brake pedal --> then release the brake pedal to let the car go downhill and fully press accelerator pedal again 4. Executing repeat 3 times in each mode Eco/ Normal/Sport Expected Result: 1.2.3.4 Normal driving No error/fail observe on MHU and vehicle No observe D2N or Limp-home No abnormal noise Actual Result: At t=211 Observe the positive packcur whereas full pressing the acc pedal and the vehicle is rolling forward with gear R. Recovery: - Occurrences: 3/5 times
[VF7 NP LHD][ FRS 7C.1.4.0 V3]: BrakeSwitch Status is always Unpressed | VN - Viet Nam | Test Sequence: 1. Test preconditions are followed. 2. Press Brake 3. Monitor WCBS_BrkPedalSwSts and Vehicle_Operation_State Expected: WCBS_BrkPedalSwSts = Pressed and Vehicle_Operation_State change to ON. Actual: WCBS_BrkPedalSwSts is always Unpressed and Vehicle_Operation_State still change to ON.
[EEC] [VF7NP] [LHD] [FRS7C.1.4.0 V4] No air blown from blower when controlled via MHU | VN - Viet Nam | 1. Precondition: Vehicle is ON Gearshift is in position P 2. Test Procedure: Use HVAC LO level Adjust level blower 3. Expected Result: Blower is working,hot and cold air blown from blower 4. Actual Result: No air blown from blower when controlled via MHU
FOOT ENTRANCE CLEARANCE - SECOND ROW OUTBOARD PASSENGER | VN - Viet Nam | FOOT ENTRANCE CLEARANCE - SECOND ROW OUTBOARD PASSENGER - 334mm target is 351.1 +/- 15 - NOK
Steering wheel vibration fails the VTS Target during WOT Acceleration and CD Deceleration | VN - Viet Nam | ● Title: Steering wheel vibration fails the VTS Target during Acceleration and Deceleration Project: VF7NP EP Issue Type: Vibration Priority: High Component/s: Chassis Labels: Vibration, Chassis, Steering Wheel, WOT, CD Environment: VF Hai Phong plant, ADAS track Description: During recent testing, the steering wheel vibration in the project vehicle failed the VTS target. This issue is particularly noticeable under the following conditions: ● ◦ Track: VF Hai Phong plant, ADAS track ◦ Speed and condition: Full Throttle Acceleration (WOT 10-120km/h), Coast Down Deceleration (CD 120-120kph) Steps to Reproduce: 1. a. Run the vehicle at the PG track, conduct Full Throttle Acceleration (Apply 100% Accelerator pedal) from 10-120km/h and Coast Down Deceleration (Release completely the pedals) from 120-10 km/h b. Observe for the steering wheel vibration. Expected Result: The vehicle should run smoothly without any noticeable/excessive noise and vibration. Actual Result: The steering wheel vibration of the vehicle does not meet the target, affecting customer comfort.
[EE Chassis][VF7NP_FRS 7C.1.4.0V5] EPB active when the vehicle speed exceeds the allowable threshold | VN - Viet Nam | Test Condition: 1.Vehicle is on static mode 2.System is Fault Free 3. Track test: straight Test Steps: 1. The vehicle in HV ON states 2. Gear in D with speed <3kph 3. EPB in release states 4. The dirver pull EPB switch to EPB applied*Expected Result:* 1. STAT_Terminal=ON 2. CVC_ACTGear=D 3. WCBS_EPB_Sts=Released EPB_SysStatIndReq= No Indication SS_P_Button= Not pressed 4. WCBS_EPB_Sts=Locking -> Locked EPB_SysStatIndReq= Continuous Indication SS_P_Button= Press Actual Result: At step 3, t=17,8s, when the veh spd is above 3 kmh, the driver pressed P button and EPB motor actives and clamps the rear brake disc. It was not following to specbook on code beamer Recovery: - Occurrences: Frequency: 3/5 times
VF7NP EP21 is not drivable after Calib override for gear. | VN - Viet Nam | The EP21 car at the PT shop is not drivable. The gear status changes as per request and calib override. MHU changes for the Gear Status. Reverse shows the rear view camera. But no movement in Vehicle after pressing accelerator.
VF7NP EP21 - Air distrubtion flap postion not as expected | VN - Viet Nam | Percentage of BCM feedback is not in as per calibrated values. Flap modes are tested for 5 cases: Face, Face + Foot, Foot, Defog (Face + Defrost), Defrost Only Face Test case has BCM feedback as expected, the others do not.
[VF7NP FRS 7C.1.4.0V6][Charging] MHU still show gun plug in even though tester unplugged | VN - Viet Nam | ● Pre-condition: ● ◦ Charger: ABB 11kW ◦ FRS 7C.1.4.0V6 ◦ DID; LTM-144452 Step: ● ◦ Vehicle is in HVon/ACC/OFF State ◦ Plugin the charge gun ◦ Stop charge and plug out charge gun ◦ Check CAN signal and MHU Expect Result: ● ◦ After stop charge and plug out charge gun, MHU display correct information Actual Result: ● ◦ After plug out charge gun, MHU still show charge gun plug in
[ePT]VF7(NP)_FRS 7C.1.4.0 V6_The vehicle can change gear from N to D/R when Press ACC Pedal | VN - Viet Nam | Test Condition: 1. Test preconditions are followed. 2. Vehicle Speed: VehicleSpd>VEHICLE_SPEED_TH (3kmph) 3.Release ACC pedal 4. Shift the gear to N 5. Press ACC and shift the gear to R/D again 6. Monitor the signal CVC_ACTGear Expected Result: 4. Gear should change to N ABS_VehicleSpeed>3 km CVC_AccPedalPosition<2% (Released) EKS_GearReq =N CVC_ACTGear = D/R=>N 4. Gear should not change to D and remain in N ABS_VehicleSpeed>3 km CVC_AccPedalPosition>2% (Released) EKS_GearReq =D/R CVC_ACTGear = N Actual Result: With step 4: The vehicle still change gear from N to D/R when Press ACC Pedal. Recovery: - Occurrences: Always
[VF7NP][EP21] EVCC Charging Component Fault | VN - Viet Nam | Cannot charge the vehicle. After the gun is plugged in, the EVCC charging status changes to Level 4 and charging fails. CAN Log: 1PT2BDY3CHS
[ePT]VF7(NP)_FRS 7C.1.4.0 V6_Auto release EPB when change from P to R and without pressing ACC pedal | VN - Viet Nam | Test Condition: 1. Vehicle in P gear 2. Change to R gear, EPB is applied 3. Press ACC Pedal >ACC_PDEAL_RELEASED_TH (2%) 4. Monitor the signal EPB Sts Expected Result: 3. EPB_Sts =Unlock EPB auto release within RELEASE_EPB_MAX_TIME_TH (1500ms) Actual Result: With step 2: Auto release EPB when change from P to R and without pressing ACC pedal Recovery: - Occurrences: Always
[ePT]VF7(NP)_FRS 7C.1.4.0 V6_The vehicle still requires torque when shifting from D/R to P and vehicle jerks | VN - Viet Nam | Test Condition: 1. Test preconditions are followed. 2. Vehicle Speed: VehicleSpd<3 km 3. Shift the gear form R/D to P 4. Monitor the signal CVC_ACTGear Expected Result: With step 3: Gear should change to P. Vehicle does not move and jerks Actual Result: With step 3: The vehicle still requires torque when shifting from D/R to P and vehicle jerks Recovery: - Occurrences: Always
EE_TnV_[VF7_NP_EP33_7C.1.4.0 TPV6] Cannot change Regen Mode when using the Stalk Switch with the Regenerative Braking option | VN - Viet Nam | VF7NP EP33 RLLV3F5D9SL200233_FRS 7C.1.4.0 TPV6 I.Precondition 1.The vehicle can move normally. 2.Vehicle is HV ON status. 3.Select the ‘Regenerative Braking’ option for Right Stalk Tip Customization on the MHU. II.Test Step 1.Rotate the Stalk Switch upward and rotate it downward. 2.Observe whether the Regen Mode setting on the MHU & IPC status & CAN signals changes. III.Test Expected 2.The Regen Mode setting on the MHU & IPC status & CAN signals should change when rotating the Stalk Switch upward and downward. IV.Actual Result 2.The Driver Mode setting changes instead of the Regen Mode. ** => FAILED V.Frequency: Always VI.Exact time Issue Happens Issue happen: from 19h45 - 09/Mar/2026 VII.Refer Video [^regen mode by stlak sw.mp4] VIII.Requirement: IX.Recover method (If have) N/A X.Remark: N/A
VF7 US : Replan DVP – Ground Clearance NOK | US - United States of America (the) | Ground clearance @ curb 170mm NOK
EE_TnV_[VF7_NP_EP34_7C.1.4.0 TPV8] After charging DC in progress, MDU it not show charging information | VN - Viet Nam | VF7NP EP34 RLLV3F5D9SL200234_FRS 7C.1.4.0 TPV8 I.Precondition 1.The vehicle can move normally. 2.Vehicle is HV ON status. 3. SOC target > SOC current. II.Test Step 1. Connect DC charge gun. 2. Waiting charging in progress and check MDU display III.Test Expected 1. Charging in progress however in MDU shall have display charging information. IV.Actual Result 1. Charging information is not display on MDU => FAILED V.Frequency: Only first cycle after ignition ON vehicle and charging VI.Exact time Issue Happens Issue happen: from 15:00 - 11/Mar/2026 VII.Refer Video VIII.Requirement: In attachment IX.Recover method (If have) N/A X.Remark: N/A
EE_TnV_[VF7_NP_EP34_7C.1.4.0 TPV8] After stop AC/DC charging, MDU always show "connection with vehicle is interrupt" and "stop charge" still display | VN - Viet Nam | ● VF7NP EP34 RLLV3F5D9SL200234_FRS 7C.1.4.0 TPV8 I.Precondition 1.The vehicle can move normally. 2.Vehicle is HV ON status. 3. SOC target > SOC current. II.Test Step 1. Connect DC charge gun. 2. Waiting charging in progress. 3. Lock vehicle by key fob. 4. Stop charging on MDU III.Test Expected 1,2. Charging is in progress. 3. Vehicle is in OFF mode. 4. Charging complete, no fault should be show on MDU, stop charge should not display after user stop charging IV.Actual Result 4. When charging is completed, charge gun show red with alert " Connection with vehicle is interrupt", "stop charge" still displayed on MDU => FAILED V.Frequency: Always VI.Exact time Issue Happens Issue happen: from 15:06 - 11/Mar/2026 VII.Refer Video In attachment ● VIII.Requirement: IX.Recover method (If have) N/A X.Remark: N/A
VF7NP_Steering wheel vibration above 100kmph | ID - Indonesia | During recent testing at indonetia, high vibration was observed on steering wheel while driving vehicle in acceleration condition as per below- ● Test condition: Acceleration test ● Track: High speed track ● Vibration observed: above 100kph Expected Result: The vehicle should accelerate smoothly without any vibration or shaking.
[VF7 NP LHD][ FRS 7C.1.4.0 V8]: Motor Torque at static condition greater than PRE_LOAD_TRQ | VN - Viet Nam | Precondition Creep Mode ON, Gear P. Description 1. Test preconditions are followed. 2. Press the break (CVC_StsBrakePedalSwitch = pressed) 3. Shift the gear to D/R 4. Monitor the torque. Expected: In static condition, the motor torque should remain ≤ 3 Nm, but it increases. Actual: CVC_FMCU_TargetTqReq = 3.2Nm at gear D.
[EE Chassis][VF7NP_FRS 7C.1.4.0V8] Abnormal noises when turn to the left at gear D | VN - Viet Nam | I. Pre-condition: 1. Vehicle Run condition 2. Battery voltage in proper range II. Step test: 1.Turn the wheels completely to the left while vehicle is stationary 2. Leave the steering wheel and drive the vehicle in creep III. Expect result: 3.Steering wheel and wheels should return to it's center position without any driver effort IV. Actual Result: Abnormal noises when turn to the left at gear D
[EE Chassis][VF7NP_FRS 7C.1.4.0V8] Abnormal noise under chassis when accelerating the vehicle | VN - Viet Nam | Test Condition: 1. Vehicle speed above 30 Km/h 2. Regen: Low 3. No fault in system Test Steps: 1. Drive the vehicle with speed above 30 Kmh ( VehicleSpd) 2. Apply the brakes with 40% 3. Check EBD status ( EBD_Active) 4. Drive the vehicle normally Expected Result: 1. Check the vehicle speed (WCBS_Vehiclespeed) 2. Check % brake pedal (WCBS_Brkpedalpct) 3. Check for EBD EBDActive =active 4. No abnormal noise Actual Result: Abnormal noise happens after hard braking and accelerating the vehicle again. Video: [^MicrosoftTeams-video.mp4] Recovery: - Occurrences: 3/5 times
[EE_Dynamic]_[VF7NP_FRS 7C.1.4.0 V8]_Drive system fault while driving normally | VN - Viet Nam | I. Pre-conditions 1. Vehicle stationary, HV ready state 2. No fault in system 3. Door and seatbelt closed 4. Drive mode: Sport/Normal/Eco II. Test Steps 1. Vehicle in standstill status with P gear 2. Change gear from P to D then drive on the traffic jam road (jam in city road) 3. Accelerbration to 30-60 km/h in 30 mins with some type of road like that straight line and turn left/ turn right 4. Drive the vehicle with some type of road like that slope in 15 mins 5. Stop the vehicle and charging 15 mins the continue drive the vehicle with speed 30-60Km/h in 30 mins 6. Vehicle in standstill status with P gear 7. Change gear from P to D then drive on the traffic jam road (jam in city road) 8. Accelerbration to 30-60 km/h in 30 mins with some type of road like that straight line and turn left/ turn right 9. Drive the vehicle with some type of road like that slope in 15 mins 10. Stop the vehicle and charging 15 mins the continue drive the vehicle with speed 30-60Km/h in 30 mins III. Expected Result Normal driving No error/fail observe on MHU and vehicle No observe D2N or Limp-home No abnormal noise IV. Actual Result At step 2, while driving like city traffic condition, vehicle faced driving system fault, motor over temp and limphome (not all at once). At some cases, the motor temprerature signal record an abnormal spike right before the vehicle entering limphome. V. Frequency 1/5 times VI. Recovery Temporary fix by clear DTC
[EE_Dynamic]_[VF7NP_FRS 7C.1.4.0 V8]_Vehicle cannot change gear | VN - Viet Nam | I. Test Condition 1. Vehicle_Operation_State= 3 (e-Motor Running). 2. Vehicle is in Dynamic Condition 3. System is Fault Free 4. Track test: Dry asphalts 5. Regen: High II. Test Steps 1. Vehicle in standstill status with P gear 2. Change gear from P to D then drive on the traffic road (city driving condition) 3. Accelerbration to 30-60 km/h in 30 mins with some type of road like that straight line and turn left/ turn right. III. Expected Result 1.2.3.4: Normal driving No error/fail observe on MHU and vehicle No observe D2N or Limp-home No abnormal noise IV. Actual Result Finishing step 3, after change gear to P, vehicle cannot change gear as video. V. Frequency Once VI. Recovery Hard reset
[VF7 NP] [FRS 7C.1.6.0 TPV2] [Network]: BCM_WindowsFR_Status (ID 0x0B5) Alive Counter Rolling Sequence & Checksum Mismatch | VN - Viet Nam | Precondition: HV ON Step: ● Record CAN log ● Monitor message ID 0x0B5 (BCM_WindowsFR_Status) ● Check alive counter behavior Expected Result: Alive counter should increment according to CAN FD V.2.0.1 specification (rolling sequence). Actual Result: Alive counter remains at 0 and does not increment, causing continuous rolling sequence mismatch errors. Reference: -DBC: [CCB-18342 [VF6/7_NewPlatform] Network Package release for PTO V3.2.5 - VinFast TMS¦https://tms.vinfast.vn/browse/CCB-18342?jql=text%20~%20%22V3.2.5%22] [VF6/7_NewPlatform] Network Package release for PTO V3.2.5 - VinFast TMS
VF7NP_EP31_NVH_Unstructured_Testing_Front_Under_Hood | VN - Viet Nam | ● What happened? ● VF7 NP EP31 vehicle unstructured testing done and Under hood plastic trims is rattling Why is it a problem? ● Plastic trims not in fixed/fastened condition ● cause squeak and rattle during vehicle operation When it happened? ● During testing at Haiphong Who detected? Nguyễn Xuân Huy - VT&V Lakshumanan Muthu Ram- Attribute Where detected? ● Haiphong Vehicle Lab How detected? ● Tested for unstructured testing in idle condition and driving condition
VF7NP_EP31_NVH_Unstructured_Testing_NVH_Interior_IP | VN - Viet Nam | ● What happened? ● VF7NP EP31 vehicle unstructured testing done and IP & console plastic trims is rattling Why is it a problem? ● Plastic trims not in fixed/fastened condition ● cause squeak and rattle during vehicle operation When it happened? ● During testing at Haiphong Who detected? Nguyễn Xuân Huy - VT&V Lakshumanan Muthu Ram- Attribute Where detected? ● Haiphong Vehicle Lab How detected? ● Tested for unstructured testing in idle condition and driving condition
VF7NP_EP31_NVH_Unstructured_Testing_Wiper | VN - Viet Nam | ● * What happened? ● Unstructured Testing for NVH performed for VF7 NP EP31 and found that Wiper arm is hitting with Hood Upper Why is it a problem? ● This creates abnormal operational hitting noise while lifting arm manually When it happened? ● 23/03/2026 Who detected? -Nguyễn Xuân Huy [VT&V] -Lakshumanan Muthu Ram [Attribute] Where detected? -Vehicle Lab, Haiphong How detected? -Unstructured static test
VF7NP water tightness exterior concern position | VN - Viet Nam | ● What happened? Issue1: Decompression vent: All rain test case Hypothesis RCA: Poor fiting: EP2#14 Issue2: ROCKER_CLIP_SUIT_HOLE: All rain test case Hypothesis RCA: Part quality: water through clip of spoiler, spoiler is 3D part Issue3: REAR_BUMPER_UPPER_BODY (both side): Vehicle tilted Hypothesis RCA: Part quality: water through clip of clip of bumper bracket Issue4: REAR_BUMPER broken: wading test 150mm 30km Hypothesis RCA: Part quality/ part missing: 3D rear bumper part, missing rear undertray Why is it a problem? Water ingress insinde cabin/Part damage Who detected? -VTnV-Reliability-Tightness Where detected? -Rain test: Rain chamber Vehicle Lab HP plant -Wading test: Wading track Vit Lab HP plant
[EEIV_VF7NP_PLUS_AWD_VN_FRS 7C.1.6.0 TPV2] Can not hard reset MHU with 11 01 | VN - Viet Nam | Precondition: - Vehicle state: HV ON - Gear at P Test produce: 1. Hard rest MHU with 11 01 2. Monitor MHU behavior Expectation: 2. Can hard reset MHU with 11 01 Actual: 2. Can not hard reset MHU with 11 01 Video: [^Video1.mp4] Time observed: 15h16' on 1st Apr 2026 Recover: Can not recover Impact: Impact to EOL process
[EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV2] There is no object behind the left side of the vehicle, but the Parking Assist warning is still activated | VN - Viet Nam | ● Precondition: - Vehicle state: HV ON - Gear at P - There is no object or person near the rear left side of the vehicle Test produce: 1. Change gear R 2. Monitor MHU behavior Expectation: 2. Parking Assist warning is not activate Actual: 2. Parking Assist warning activated Time observed: 12h00' on 1st Apr 2026 Video: [^ParkingAssist.mp4] Recover: Can not recover Impact to customer: The customer may misunderstand that there is a person or obstacle behind the vehicle, leading to wasted time checking in reality
[EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV2] Can not write VIN DCDC | VN - Viet Nam | ● Precondition: - Vehicle state: HV ON - Gear at P Test produce: 1. Write VIN DCDC: 52 4C 4C 56 33 46 55 56 38 54 48 37 32 35 34 39 32 2. Monitor VIN DCDC after Write by CBT tool Expectation: 2. Can Write VIN DCDC 52 4C 4C 56 33 46 55 56 38 54 48 37 32 35 34 39 Actual: 2. Can not Write VIN DCDC: Time observed: 13h32' on 2nd Apr 2026 Recover: Can not recover Impact: Impact to EOL process
[EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV2] Can not write VIN MCU | VN - Viet Nam | ● Precondition: - Vehicle state: HV ON - Gear at P Test produce: 1. Write VIN MCU: 52 4C 4C 56 33 46 55 56 38 54 48 37 32 35 34 39 32 2. Monitor VIN MCU after Write by CBT tool Expectation: 2. Can Write VIN MCU 52 4C 4C 56 33 46 55 56 38 54 48 37 32 35 34 39 Actual: 2. Can not Write VIN MCU : Time observed: 13h32' on 2nd Apr 2026 Recover: Can not recover Impact: Impact to EOL process
[EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV2] Can not write VIN OBC | VN - Viet Nam | ● Precondition: - Vehicle state: HV ON - Gear at P Test produce: 1. Write VIN OBC: 52 4C 4C 56 33 46 55 56 38 54 48 37 32 35 34 39 32 2. Monitor VIN OBC after Write by CBT tool Expectation: 2. Can Write VIN OBC 52 4C 4C 56 33 46 55 56 38 54 48 37 32 35 34 39 Actual: 2. Can not Write VIN OBC: Time observed: 13h32' on 2nd Apr 2026 Recover: Can not recover Impact: Impact to EOL process
[EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV2] Can not write VIN DSCU | VN - Viet Nam | [EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV2] Can not write VIN DSCU
[EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV2] AC auto turn ON after turn on Fan mode - Not follow requirement | VN - Viet Nam | Precondition: - Vehicle state: HV ON - Gear at P - AC = Off - Fan mode = Off (Level 0) Test produce: 1. Adjust Fan mode to any level 1/2/3/4/5/6 2. Monitor AC behavior on MHU Expectation: 2. AC not turn ON after turn on Fan mode Actual: 2. AC auto turn ON after turn on Fan mode Requirement: Time observed: 16h09' on 3rd Apr 2026 Video: [^ACTurnOnAfTurnOnFanLevel.mp4] Recover: NA Impact: Not follow requirement
EE_TnV_[VF7_PTO_Vin5492_7C.1.6.0 TPV4] When AVH is active, the IPC displays a vehicle speed of 1 kmh while WCBS_VehicleSpeed = 0 kmh | VN - Viet Nam | VF7NP PTO RLLV3FUV8TH725492_FRS 7C.1.6.0 TPV2 I.Precondition 1.The vehicle can move normally. 2.Vehicle is HV ON status. 3.AVH function is normal working. II.Test Step 1.Activate AVH when the vehicle is on an uphill, downhill, and flat surface 2.Observe on MHU, IPC, and CAN signals III.Test Expected 2.When AVH is active, the vehicle speed displayed on the IPC and transmitted via CAN signals shall be 0. IV.Actual Result 2.When AVH is active, the IPC displays a vehicle speed of 1 km/h while WCBS_VehicleSpeed = 0 km/h under uphill, downhill, and flat conditions. => FAILED V.Frequency: Always VI.Exact time Issue Happens Issue happen: from 06h06 - 06/Apr/2026 VII.Refer Video Attached VIII.Requirement: IX.Recover method (If have) N/A X.Remark: N/A
[VF7NP_VN_VTnV_PQ] - Headrest lacks dual curvature | VN - Viet Nam | ● * What happened? ● Headrest lacks dual curvature ● Why is it a problem? ● Headrest lacks dual curvature → limited support across user heights ● When it happened? ● April 3rd ● Who detected? - Thengungal Wilson Simson ● Where detected? ● VinUniversity ● How detected? ● Observing & Testing ● How many failure? ● 1/1 vehicle
[EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV3] Front camera at gear D no have guideline | VN - Viet Nam | Precondition: - Vehicle state: HV ON - Gear at P Test produce: 1. Change gear to R then change gear to D 2. Monitor MHU behavior Expectation: 2. Front camera at gear D have guideline Actual: 2. Front camera at gear D no have guideline *Note: Rear camera at gear R no have guideline same Front camera at gear D Requirement: Time observed: 20h51' on 8th Apr 2026 Video: [^Front.RearCamNoGuideline.mp4] Recover: NA Impact: Not follow requirement
[EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV3] Not appear warning Anti-theft after Use Mechanical Key to open Driver door | VN - Viet Nam | Precondition: - Vehicle state: HV ON - Gear at P Test produce: 1. All doors closed and all doors locked 2. Lock vehicle by Key Fob and Do not leave the keys in the car 3. Use Mechanical Key to open Driver door 4. Monitor vehicle behavior Expectation: 2. Appear warning Anti-theft Actual: 2. Not Appear warning Anti-theft after Use Mechanical Key to open Driver door Requirement: Time observed: 14h49' on 9th Apr 2026 Video: [^AntitheftNotWork.mp4] Recover: NA Impact: Related to safety. For example: a family is sleeping inside a car, and someone opens the car door using a mechanical key or a similar tool and then engages in harmful behavior—this would pose a danger to the people inside the vehicle.
[EE Dynamic]_VF7NP_FRS 7C.1.6.0 TPV3_VN_Error Fan speed control error on the MHU | VN - Viet Nam | I. Pre-condition: 1. Car is fully updated to target SW baseline. 2. LV is at good level 3. No error/fail message on MHU screen and vehicle. 4. Gear shifts in P position 5. All function off, all door closed II. Test Condition: 1. Turn on Overhead Lighting Driver or Passenger 2. Set AC to min temperature ( fan 4) 3. Go out and press lock keyfob to vehicle sleep 4. Waiting till Overhead Lighting Driver or Passenger off 5. Press unlock keyfob and press break 6. Set AC to min temperature ( fan 4) 7. Repeat 5 times III. Expect result: 'Vehicle sleep/wake-up nomarlly No error/fail observe on MHU and vehicle No observe D2N or Limp-home IV. Actual result: At step 2: Unable to adjust the fan speed as desired: setting level 3 reverts to level 2, level 4 reverts to level 3, while levels 5 and 6 remain unchanged. [^MicrosoftTeams-video.mp4] V. Frequency: Always VI. Recovery Can't recover
EE_TnV_[VF7NP_PTO_Vin5510_7C.1.6.0 TPV3] No fault warnings for WCBS brake-related systems are displayed after removing the brake fluid sensor connector | VN - Viet Nam | VF7NP PTO RLLV3FUV6TH725510 FRS 7C.1.6.0 TPV3 I.Precondition 1.The vehicle can move normally. 2.Vehicle is HV ON status. 3.All brake systems work normally. 4.Turn on AVH function on the MDU. II.Test Step 1.Disconnect the brake fluid sensor connector. 2.Press the brake pedal, shift to D/R, and drive the vehicle. 3.Observe brake system warning messages displayed on the MDU and IPC. III.Test Expected 3.Brake-related systems dependent on WCBS will display system fault warnings on the MDU & IPC (e.g., ABS, ESC, HSA, HBA, AVH, ...) IV.Actual Result 3.Only the “Brake Fluid Low” warning is displayed; no other brake system fault warnings are shown on the MDU, IPC, or in the DTC. => FAILED -DID of WCBS before execution: -DID of WCBS after remove connector: -Warnings are not fully displayed on the MDU and IPC V.Frequency: Always VI.Exact time Issue Happens Issue happen: from 21h25 - 12/Apr/2026 VII.Refer Video [^not warning brake sys.mp4] VIII.Requirement: IX.Recover method (If have) N/A X.Remark: N/A
[ePT]VF7(NP)_FRS 7C.1.6.0 V3_ The "EPS error" warning appears on MHU when turn left, turn right | VN - Viet Nam | Test Condition: 1. Vehicle in Engine start 2. Press brake and change gear D. 3. Press Acc pedal the vehicle to certain speed(30 km/h). 4. Turn left vehicle, Turn right vehicle 5. Check signal Can Expected Result: Turn left vehicle, Turn right vehicle normally No error, No Warning. Actual Result: With step 4: The "EPS error" warning appears on MHU when turn left, turn right Recovery: - Occurrences: Always
[VF7_NP] [7C.1.6.0TPV3]: FPA: it doesn't display on the MHU in spite of enabling FPA coding | VN - Viet Nam | Procedure: 1. Open Trợ lái 2. Observe on the MHU Expect: As per feature list confirmation Actual: It doesn't display on the MHU in spite of enabling FPA coding
[VF7_NP] [7C.1.6.0TPV3]: TSR: There isn't haptic function on the MHU | VN - Viet Nam | Expect: There is haptic TSR function on the MHU Actual: There isn't haptic function on the MHU DID: LTM-155030 Baseline: -SYS1: https://vgrts.vinfast.vn/cb/tracker/12325296?revision=25279684&view_id=-2 -UIUX: https://vgrts.vinfast.vn/cb/tracker/9216221?view_id=-2&revision=25518268 Log MHU: VF7NP-5365 [VF7_NP] [7C.1.6.0TPV3]: ADAS: Driving assistance, Quick Access icon is different with the design - VinFast TMS
[EE-FOTA_VF7NP_VN_FRS 7C.1.6.0 TPV3]HV Lost After Downgrade BMS to Dummy, HV Recovered by LV reset | VN - Viet Nam | Issue Description Steps: 1- BMS Campaign Deployed 2- Campaign Download Success 3- FOTA Installation Success 4- Lost HV after FOTA Recovery: LV Reset Actual Result: HVLost AfterFOTA install Expected Result: HVONafter FOTA Install
[VT&V_NVH] Rattle noise form FL door trim | VN - Viet Nam | ● * What happened? ● Rattle noise form FL door trim ● Why is it a problem? ● Abnormal noise, impact to customer experience ● When it happened? ● 15 Apr 2026 ● Who detected? ● TuanQM ● Where detected? ● SR Track, HP Factory ● How detected? ● Drive at rough road ● How many failure?
[VT&V_NVH] Warning chime volume is too loud | VN - Viet Nam | ● * What happened? ● Warning chime volume is too loud ● Why is it a problem? - ● When it happened? - 15 Apr 2026 ● Who detected? ● TuanQM ● Where detected? - ● How detected? - ● How many failure?
[Thermal AVTV - Thermal Lab][VF7NP-LHD][FRS 7C.1.6.0 TPV3] CoolantTemp EDS In ( WT2) sensor feedback is not the correct value | VN - Viet Nam | 1. Testing Environment: 1. a. ** We setup the sensor and connect the 6in1 coolant loop to heat change system and read value sensor by AVL system as below image. b. UUT: VF7NP Bench at Thermal lab. 2. Precondition 1. a. Bench in Ready mode b. 6in1 works normally. c. Coolant temperature is 25 degrees. BCMFL_CoolantTemp_EDS_In = 25 ℃. BCMFL_CoolantTemp_EDS_Out = 25 ℃. Coolanttemp_6in1_Outlet_Lab ( lab sensor) = 25 ℃. Coolanttemp_6in1_Intlet_Lab ( lab sensor) = 25 ℃. 1. a. Set Pump 1 works at 50% PWM. 2. Testing Step 1. Change the coolant temperature from 25 ℃ to 60 ℃ as 5 ℃ a step. After that decrease the coolant temperature from 60 ℃ to -20 ℃ as 5 ℃ a step. Wait over 3 minutes at each step for the temperature to stabilize. 2. Log all data from sensor. 1. Test expected 1. The measured temperature from BCMFL_CoolantTemp_EDS_In shall match the reference sensor (Coolanttemp_6in1_Intlet_Lab) within the acceptable tolerance range (± 2°C). Any deviation beyond this limit shall be considered a failure. 2. The measured temperature from BCMFL_CoolantTemp_EDS_Out shall match the reference sensor (Coolanttemp_6in1_Out_Lab) within the acceptable tolerance range (± 2°C). Any deviation beyond this limit shall be considered a failure. 1. Test actual. Refer this report file for more detail - [^CoolantSensorComparation_20260413_VF7NP_ThermalLab.pdf] BCMFL_CoolantTemp_EDS_Out : PASSED – within tolerance. BCMFL_CoolantTemp_EDS_In: FAIL - deviation exceeds 10°C tolerance.For exmaple, when Lab sensor reachs 60 ℃ in over 5 mins, BCMFL_CoolantTemp_EDS_In only reachs 50 ℃ and the Lab sensor decreases to -20 ℃, BCMFL_CoolantTemp_EDS_In only reachs 3 ℃.℃
[ePT]VF7(NP)_FRS 7C.1.6.0 V3_ "Connection interrupted" Warning on MHU while turn off vehicle | VN - Viet Nam | Test Condition: 1 Turn on vehicle by key-fob 2. Changed gears to D/R/N 3. Turn off vehicle by key-fob (make sure that key-fob not inside the vehicle) Expected Result: 'Vehicle sleep/wake-up normally No error/fail observe on MHU and vehicle No observe lost HV, Drv system fault Actual Result: With step 3: "Connection interrupted" Warning on MHU while turn off vehicle Recovery: - Occurrences: Always
[ePT]VF7(NP)_FRS 7C.1.6.0 V3_ The warning will continuously alarm when the vehicle is turned off. | VN - Viet Nam | Test Condition: 1 Turn on vehicle by key-fob 2. Changed gears to D/R/N 3. Turn off vehicle by key-fob (make sure that key-fob not inside the vehicle) Expected Result: 'Vehicle sleep/wake-up normally No error/fail observe on MHU and vehicle No observe lost HV, Drv system fault Actual Result: With step 3: The warning will continuously alarm when the vehicle is turned off. Pls confirm video Recovery: Warning will stop when vehicle is deep sleep Occurrences: Always
[EEC] [VF7NP-LHD] [FRS 7C.1.6.0 TPV4] BMS active cooling doesn't work | VN - Viet Nam | After flashing new version of SW"FRS 7C.1.6.0 TPV4" on thermal bench,pumps don't response to commands requested by ECUs correctly.
[VF7_NP] [7C.1.6.0TPV3]: Lane Assist does not switch back to ON after factory reset MHU. | VN - Viet Nam | Procedure: 1. Turn OFF Lane Assist on MHU 1. Factory reset 2. Observe on the MHU Expect: Lane Assist turn ON after factory reset MHU. Actual: Lane Assist does not switch back to ON after factory reset MHU. Time: 4/17/2026 (14:27:19- 14:32:06 PM) Link: DID, DTC, Coding: LTM-155030 Update new FRS 7C.1.6.0 V3 for VF7NP VN VIN RLLV3FUV6TH725507 - VinFast TMS Link evidence: EMT-213574 Sub-task - Log ADAS setting 1704 - VinFast TMS
[VF7_NP] [7C.1.6.0TPV3]: Emergency Lane Keeping Haptics Settings does not switch back to ON after factory reset MHU. | VN - Viet Nam | Procedure: 1. Turn OFF Emergency Lane Keeping Haptics Settings on MHU 1. Factory reset 2. Observe on the MHU Expect: Emergency Lane Keeping Haptics Settings turn ON after factory reset MHU. Actual: Emergency Lane Keeping Haptics Settings does not switch back to ON after factory reset MHU. Time: 4/16/2026 (16:44:59- 16:48:16 PM) Link: DID, DTC, Coding: LTM-155030 Update new FRS 7C.1.6.0 V3 for VF7NP VN VIN RLLV3FUV6TH725507 - VinFast TMS Link evidence: EMT-213467 Sub-task - Log ADAS setting 16042026 - VinFast TMS
[VF7NP FRS 7C.1.6.0V3][Charging] MHU show incorrect SOC parameter when wakeup vehicle | VN - Viet Nam | Pre-conditions: 1. FRS7C.1.6.0V3 2. Charging station: All 3. DID: LTM-154629 Step: 1. Vehicle in sleep mode 2. Set target SOC > current SOC 3. Plug in charge gun 4. Check CANsignal and MHU during charging 5. Wakeup vehicle Expect Result: ● Vehicle can charge normally after plug in charge gun ● Wake up normally without error Actual result: ● After wake up, MHU report SOC is less than 20%, actually SOC is differrent
[EE-FOTA_VF7NP_VN_FRS 7C.1.6.0 TPV3]HV Lost After Atomic FOTA Installation, Recovered by LV reset | VN - Viet Nam | Issue Description Test preconditions: 1. Campaign ready for install Test steps: 1. Press install 2. Install successful and reboots 3. Press brakes Expected: After press brakes, HV is ON and MHU screen displays Ready Actual: After press brakes, HV is OFF and Ready Unavailable Detail Occurrence: 1/1/1 Recover actions: Battery Reset Lost HV After FOTA: 4 campaign
[VF7_NP] [7C.1.6.0TPV3]: DOW: DOW still sets OFF after factory reset | VN - Viet Nam | Procedure: 1. DOW setting sets OFF 2. Factory reset MHU 3. Observe DOW setting Expect: DOW setting sets ON after factory reset Actual: DOW setting still sets OFF after factory reset Time: 04:48 pm 17/04/2026 Log Can + Video + MHU + CVC: EMT-213467 DID: LTM-155030
[VF7_NP] [7C.1.6.0TPV3]: FCW: FCW setting still sets OFF after factory reset | VN - Viet Nam | Procedure: 1. FCW setting sets OFF 2. Factory reset MHU 3. Observe FCW setting Expect: FCW setting sets ON after factory reset Actual: FCW setting still sets OFF after factory reset Time: 04:48 pm 17/04/2026 Log Can + Video + MHU + CVC: EMT-213467 DID: LTM-155030
[VF7_NP] [7C.1.6.0TPV3]: FCW: FCW sensitivity setting still sets High after factory reset | VN - Viet Nam | Procedure: 1. FCW sensitivity setting sets High 2. Factory reset MHU 3. Observe FCW sensitivity setting Expect: FCW sensitivity setting sets LOW after factory reset Actual: FCW sensitivity setting still sets HIGH after factory reset Time: 04:48 pm 17/04/2026 Log Can + Video + MHU + CVC: EMT-213467 DID: LTM-155030
[VF7_NP] [7C.1.6.0TPV3]: TSR does not switch back to ON after factory reset MHU. | VN - Viet Nam | Procedure: 1. Turn OFF TSR on MHU 1. Factory reset 2. Observe on the MHU Expect: TSR turn ON after factory reset MHU. Actual: TSR does not switch back to ON after factory reset MHU. Time: 4/17/2026 (14:27:26- 14:33:27 PM) Link: DID, DTC, Coding: LTM-155030 Update new FRS 7C.1.6.0 V3 for VF7NP VN VIN RLLV3FUV6TH725507 - VinFast TMS Link evidence: EMT-213574 Sub-task - Log ADAS setting 1704 - VinFast TMS
[VF7NP][VN][FRS 7C.1.6.0 TPV4] IPC weather widget displays incorrect information compared to MHU. | VN - Viet Nam | 1. Test Precondition 1.Vehicle state = ON 2. Test Steps 1. Observe the MHU and IPC 3. Expected Result 1. IPC weather widget displays incorrect information compared to MHU. 4. Actual Result 1. IPC weather widget displays correct information compared to MHU. 5. Exact time issue happens 15:09 17/4/2026 6. Reference: IPC Entertainment feature list N-UIUX6789-3006562
[VF7_NP] [7C.1.6.0TPV3]: Lane Assist Steer Mode Settings does not switch back to OFF after factory reset MHU. | VN - Viet Nam | Procedure: 1. Turn ON Lane Assist Steer Mode Settings on MHU 2. Factory reset 3. Observe on the MHU Expect: Lane Assist Steer Mode Settings turn OFF after factory reset MHU. Actual: Lane Assist Steer Mode Settings does not switch back to OFF after factory reset MHU. Time: 4/17/2026 - (14:36:30 - 14:39:43) Link: DID, DTC, Coding: LTM-155030 Update new FRS 7C.1.6.0 V3 for VF7NP VN VIN RLLV3FUV6TH725507 - VinFast TMS Link evidence: EMT-213574 Sub-task - Log ADAS setting 1704 - VinFast TMS
[VF7_NP] [7C.1.6.0TPV3]: Emergency Lane Keeping Settings does not switch back to OFF after factory reset MHU. | VN - Viet Nam | Procedure: 1. Turn ON Emergency Lane Keeping Settings on MHU 2. Factory reset 3. Observe on the MHU Expect: Emergency Lane Keeping Settings turn OFF after factory reset MHU. Actual: Emergency Lane Keeping Settings does not switch back to OFF after factory reset MHU. Time: 4/17/2026 - (14:36:37 - 14:40:26) Link: DID, DTC, Coding: LTM-155030 Update new FRS 7C.1.6.0 V3 for VF7NP VN VIN RLLV3FUV6TH725507 - VinFast TMS Link evidence: EMT-213574 Sub-task - Log ADAS setting 1704 - VinFast TMS
[VF7_NP] [7C.1.6.0TPV3]: FCW sensitivity setting still sets Medium after factory reset | VN - Viet Nam | Procedure: 1. FCW sensitivity setting sets Medium 2. Factory reset MHU 3. Observe FCW sensitivity setting Expect: FCW sensitivity setting sets LOW after factory reset Actual: FCW sensitivity setting still sets Medium after factory reset Time: 4/17/2026 - (14:36:13 - 14:41:05) Link: DID, DTC, Coding: LTM-155030 Update new FRS 7C.1.6.0 V3 for VF7NP VN VIN RLLV3FUV6TH725507 - VinFast TMS Link evidence: EMT-213574 Sub-task - Log ADAS setting 1704 - VinFast TMS
[EEIV_VF7NP_VN_FRS 7C.1.6.0 TPV4] Can not Start Anti-Pinch Self Learn BCM_FR | VN - Viet Nam | Precondition: - Vehicle state: HV ON - Gear at P Test produce: 1. Create sequency Calibration of BCM_FR and start check 2. Can start Anti-Pinch Self Learn BCM_FR at step 3 Expectation: 2. Can Start Anti-Pinch Self Learn BCM_FR Actual: 2. Can not Start Anti-Pinch Self Learn BCM_FR Time observed: 14h28' on 20th Apr 2026 Recover: Can not recover Impact: Impact to EOL process
[EE Chassis][VF7NP_FRS 7C.1.6.0V3] Cannot change steering mode when changing drive mode on MHU | VN - Viet Nam | Test Condition: 1. Vehicle ON condition, HV ready state 2. Battery voltage in proper range Test Steps: 1. The vehicle park with P gear 2. Change drive mode from MHU ECO→ Normal→ Sport 3. Check status of Steering mode Expected Result: 2. Check activation signal for steering mode: CVC_ACT_Drivemode= ECO → Normal → Sport MHU_Set_Drivingmodeswitch=ECO→ Normal→ Sport EPS_SteerPrsnlMod=ECO→ Normal→ Sport ( With MHU provide full 3 modes, if MHU provide only 2 mode ( ECO=ECO; Normal = Sport) Actual Result: When the drive changes drive mode on MHU, steering mode cannot be changed and still remain at ECO mode Recovery: - Occurrences: Always
[EE Chassis][VF7NP_FRS 7C.1.6.0V3] EPB still lock when change gear from P/N to D/R | VN - Viet Nam | Pre-Condition 1.Vehicle is on static mode 2.System is Fault Free 3. Slolpegrade > 5% Test Steps: 1. The vehicle in HV ON state gear in P, EPB applied 2. Door closed and seat belt closed 3. Press brake pedal and change gear to D, EPB releases Repeat these step with GEAR R/N Expected Result: 1. Vehicle_Operation_State=ON CVC_ACTGear=P EPB_Sts=Locked EPB_SysStatIndReq = Continuous Indication 3. CVC_ACTGear=N/R/D EPB_Sts=Releasing → Released EPB_SysStatIndReq = No Indication Actual Result: At t = 907s, when the vehicle at gear P with slope = 8% (EPB apllied), change gear to D/N/R but EPB doesn't release. Recovery: - Occurrences: Always
[EE DYNAMIC][VF7NP_FRS 7C.1.6.0 V4] Abnormal noise when press acc pedal and release acc pedal | VN - Viet Nam | I. Pre-condition: 1. Vehicle stationary, HV ready state 2. No fault in system 3. Door and seatbelt closed II. Test Condition: 1. HV ON and unfasten seatbelt then open the door 2. Press Break Pedal 3. Change Gear to from P to D >> Press accelerator and release continuously 4. Change Gear to from P to R >> Press accelerator and release continuously 5. Change Gear to from P toN >> Press accelerator and release continuously III. Expect result: 1.2.3.4.5 Normal driving No error/fail observe on MHU and vehicle No observe D2N or Limp-home No abnormal noise Normal change gear IV. Actual result: At step 3: Abnormal noise when release ACC pedal [^MicrosoftTeams-video.mp4] V. Frequency: Sometimes VI. Recovery Vehicle auto recovery
DVPRXHBEX0001 ,DVPRXHBEX0002- Front and Rear Bumper assy_ failed Ultrasonic welding retention test | VN - Viet Nam | Test : Ultrasonic welding retention test as per VFDST00099000 The sample shall be peeled at a rate of 50mm/min until there is separation between the 2 pieces. Acceptance Criteria: Record Peak force of each weld pad to separate: min > 150 N or specified on drawing Test failed at VINES and refer the results below. !image-2026-04-22-11-58-45-772.png!
EE_TnV_[VF7NP_PTO_VN] Vin5510 [7C.1.6.0 TPV4] There is an abnormal warning on the MDU when the steering wheel reaches full left or right lock. | VN - Viet Nam | VF7NP PTO RLLV3FUV6TH725510 FRS 7C.1.6.0 TPV4 I.Precondition 1.The vehicle can move normally. 2.Vehicle is HV ON status. 3.The EPS system operates normally and there is no error in the DTC. II.Test Step 1.Turn the steering wheel from the center position to full left or right lock. 2.Observe the behavior on the IPC, MDU, and CAN signals. III.Test Expected 2.Turn the steering wheel smoothly, without jerking or excessive steering torque. No faults or abnormal warnings should occur on the CAN, IPC, MDU, or DTC. IV.Actual Result 3.There is an abnormal warning, ‘Restart vehicle to restore Steering Assist’ on the MDU when the steering wheel reaches full left or right lock, and the warning chime affects the driver. => FAILED V.Frequency: Always VI.Exact time Issue Happens Issue happen: from 19h56 - 22/Apr/2026 VII.Refer Video [^warning incorrect with EPS.mp4] VIII.Requirement: IX.Recover method (If have) N/A X.Remark: N/A
[EEIV_VF8NP_VN_FRS 7C.1.6.0 TPV4] MHU - Can not turn ON Pet mode | VN - Viet Nam | Precondition: - Vehicle state: HV ON - Gear at P Test produce: Step 1. ON MHU - Turn On pet mode Step 2: Monitor MHU display Expectation: Step 2. Can turn ON pet mode Actual: Step 2. Can not turn ON pet mode Time observed: 17h06' on 24th Apr 2026 Recover: Can not recover Impact: Can not turn off / turn on this function follow user requirement
[CTF_VF8NP_PTO_FRS 7C1.6.0V4] Unable to set desired fan speed level in HVAC (fan speed toggles between levels 1 and 2) | VN - Viet Nam | 1) Precondition Vehicle is in Ready state 2) Test Steps Open the HVAC (air conditioning) control menu Set the fan speed to level 1 Observe the fan speed Set the fan speed to level 2 Observe the fan speed again 3) Expected Result The fan speed should remain at the selected level (level 1 or level 2) as set by the user 4) Actual Result When setting fan speed to level 1, it automatically changes to level 2 When setting fan speed to level 2, it automatically changes back to level 1 5) Recovery Automatically recovery after driving for long time.
[Crash test] The MDU displayed a low battery warning (below 20%) while the battery level was shown as 97% immediately after unlocking the vehicle using the key fob. | VN - Viet Nam | ● * What happened? ● The MDU displayed a low battery warning (below 20%) ● Why is it a problem? ● Because the actual battery level is 97%, but the display shows a warning that the battery level is below 20%. ● When it happened? - Immediately after unlocking the vehicle using the key fob. ● Who detected? ● Crash team ● Where detected? ● Crash lab ● How detected? ● Off the vehicle until deep sleep after that turn on the vehicle by keyfob ● How many failure? 10/10
[EEC] [VF8NP-LHD] [FRS 7C.1.6.0 TPV5] AC Charging Current Limit jumps incorrectly when adjusting | VN - Viet Nam | Pre-condition: ● Vehicle in Ready Mode Test Action: ● Step 1: Connect vehicle to AC charging gun ● Step 2: Start charging and increase/decrease limit current on MHU (step by step) ● Step 3: Observer charging current value Expected Result ● Charging current limit should change smoothy (eg: 32A-->16A–>12A,...) ● Match user input exactly (1 press = 1 step) Actual Result: ● Charging current limit jump irregularly ● Does not match user input
[CTF-VN][VF8NP FRS 7C.1.6.0V4] MDU does not display the current speed and gear information. | VN - Viet Nam | Preparation Conditions Vehicle Ready MDU still displays full information 2. Testing Steps Drive the car with the engine off for more than 30 minutes, then restart the car 3. Expected Results The car starts smoothly, no errors occur, and the screen still displays full information 4. Actual Results After turning off the engine for more than 30 minutes and restarting, the MDU does not display the speed or the currently set gear Odo:3915
[VF8NP FRS 7C.1.6.0V5] Vehicle can not deep sleep after turn off | VN - Viet Nam | Pre-conditions: 1. FRS 7C.1.6.0V5 2. Charging station: All 3. DID: LTM-158563 Step: 1. Vehicle in HVon/ACC state 2. Turn off the vehicle and wait 3. When vehicle is deep sleep, plug in charge gun Expect Result: ● Vehicle can deep sleep ● Charging normally Actual result: ● Step 2, vehicle can not deep sleep
[FPT][VF8 NP][VN][FRS 7C.1.6.0 V6] The AHB setting auto turn OFF when setting ON | VN - Viet Nam | 2.1. Test Preconditions 1. Screen ON and MHU fully booted 2. Current screen is AHB setting. 2.2. Test Steps 1. Setting AHB is ON 2.3. Expected Result 1. The AHB setting turn ON normal. 2.4. Actual Result 1. The AHB setting auto turn OFF. 2.5. Exact time issue happens 16:21 2.6. Reference User's viewpoint 2.7. Recovery method NA 2.8. Remark DID/DTC: LTM-158957 Pre integration check - VF8 NP LHD VIN 5942 to FRS 7C.1.6.0_TPV6 - VinFast TMS
[EE‑FOTA_VF7NP_VN_FRS 7C.1.6.0 TPV6] EPS_SS Fota Fail go to Failsafe | VN - Viet Nam | Test preconditions: 1. Vehicle have Wifi Test steps: 1. Deploy campaign 1. Download and start install Expected: Campaign install success Actual: EPS_SS Fota Fail go to Failsafe Time issue happen: 07/05/2026 Detail Occurrence: 1/1/1 Recover actions: N/A
[EE‑FOTA_VF8NP_VN_FRS 7C.1.6.0 TPV6] BCM FOTA fail, rollback fail, go to failsafe | VN - Viet Nam | Test preconditions: 1. Vehicle have Wifi Test steps: 1. Deploy campaign 2 download and install Expected: Campaign install success no error Actual: BCM FOTA fail, rollback fail, go to failsafe Occurrence: 1/1/1 Recover actions: N/A
[EE‑FOTA_VF8NP_VN_FRS 7C.1.6.0 TPV6] SS FOTA fail, rollback fail, go to failsafe | VN - Viet Nam | Test preconditions: 1. Vehicle have Wifi Test steps: 1. Deploy campaign 2 download and install campaign Expected: Campaign install success no error Actual: SS FOTA fail, rollback fail, go to failsafe Occurrence: 1/1/1 Recover actions: N/A
[EE‑FOTA_VF8NP_VN_FRS 7C.1.6.0 TPV6] SRR FOTA fail, rollback fail, go to failsafe | VN - Viet Nam | Test preconditions: 1. Vehicle have Wifi Test steps: 1. Deploy campaign 2 download and install campaign Expected: Campaign install success no error Actual: SRR FOTA fail, rollback fail, go to failsafe Occurrence: 1/1/1 Recover actions: N/A
[EE‑FOTA_VF8NP_VN_FRS 7C.1.6.0 TPV6] MRR FOTA fail, rollback fail, go to failsafe | VN - Viet Nam | Test preconditions: 1. Vehicle have Wifi Test steps: 1. Deploy campaign 2 download and install campaign Expected: Campaign install success no error Actual: MRR FOTA fail, rollback fail, go to failsafe Occurrence: 1/1/1 Recover actions: N/A
[EE‑FOTA_VF8NP_VN_FRS 7C.1.6.0 TPV6] EVCC FOTA fail, rollback fail, go to failsafe | VN - Viet Nam | Test preconditions: 1. Vehicle have Wifi Test steps: 1. Deploy campaign 2 download and install campaign Expected: Campaign install success no error Actual: EVCC FOTA fail, rollback fail, go to failsafe Occurrence: 1/1/1 Recover actions: N/A
[Wiring harness][VF8NP] Door Speaker Connector Oriented Upward. | VN - Viet Nam | Test Environment: VF VITLAB lab, HP Test Case ID: VIT_Harness_LL_06_Stationary_1 (LLM-2045) Test Procedures: ● Step 1: Inspect on 3D for the wiring harness for check all speaker connectors location. then check all speaker connectors to verify whether they are oriented downward. ● Step 2: Ensure that all interior trims have been removed so that the vehicle wiring can be fully observed then inspect on the vehicle all speaker connectors to verify whether they are oriented downward ● Step 3: Inspect and compare the details on the 3D model with the actual vehicle. Take photos as evidence Expected Results:. ● After Step-3 : All speaker connectors are oriented downward. The wiring harness, connectors and layout shown in the 3D design perfectly match the actual configuration on the vehicle. Test Observation: ● All speaker connectors are facing upwards. Actual results: - Door speaker connectors are currently oriented upward. This configuration may allow water accumulation and ingress into the connector area, increasing the risk of corrosion, poor electrical contact, and potential speaker malfunction over time.
EE_TnV_[VF8NP_LHD_VN_VIN5494_PTO]_[FRS 7C.1.6.0 V6]_Easy Access Setting Missing and Signal Not Responding on MHU | VN - Viet Nam | 1. Precondition: The vehicle is in power ON mode. FIP function is implemented in vehicle software. No system faults are present. 2. Test Procedure: Navigate to MHU vehicle settings menu. Check for Easy Access enable/disable setting option. Operate Easy Access related function and monitor signal response level. 3. Expected Result: The MHU shall provide an option to enable/disable Easy Access function. The Easy Access signal level shall respond correctly according to user setting and system operation. 4. Actual Result: FIP is implemented, however: No Easy Access setting option is available on MHU. Easy Access signal level is not responding correctly. 5. Frequency: Always. 6. Time of Occurrence: 15h27 13/5/2026 7. Reference Video: Attached 8. Requirement Reference: Easy Access feature requirement / HMI setting specification. 9. Recovery Method: Not available. 10. Remarks: Feature implementation appears incomplete because FIP is available but related HMI configuration and signal response behavior are missing or not functional.
[FPT][VF8NP MKT][VN][FRS 7C.1.6E.2 V2] Time is incorrect when wifi not connected | VN - Viet Nam | 2.1. Test Preconditions 1. Vehicle is ON 2. Gear P 3. Auto date time and auto time zone is on 2.2. Test Steps 1. Check time on MHU 2.3. Expected Result 1. Time is correct 2.4. Actual Result 1. Time is incorrect 2.5. Exact time issue happens 8:50 15/05/26 2.6. Reference 2.7. Recovery method Connect Wifi 2.8. Remark Evidence refer ticket ** IVF8NP-9843
[FPT][VF8NP MKT][VN][FRS 7C.1.6E.2 V2] Previous app is opened when tap on VA from app library | VN - Viet Nam | 2.1. Test Preconditions 1. Vehicle is ON 2. Gear P 2.2. Test Steps 1. Tap on VA app 2.3. Expected Result 1. Vivi is activated, no app is opened 2.4. Actual Result 1. Vivi is activated and previous app is opened 2.5. Exact time issue happens 10:06 15/05/26 2.6. Reference 2.7. Recovery method NA 2.8. Remark
[FPT][VF8NP MKT][VN][FRS 7C.1.6E.2 V2] Can't adjust volume voice guidance VietMap | VN - Viet Nam | 2.1. Test Preconditions 1. Vehicle is ON 2. Gear P 3. Have internet 2.2. Test Steps 1. Open VietMap -> Navigation to any destination 2. Adjust volume when voice guidance output 3. Obser 2.3. Expected Result 3. Volume of voice guidance can be adjusted 2.4. Actual Result 3. The volume of the voice guidance is turned down to the minimum level, but the audio is still audible. 2.5. Exact time issue happens 11:23 15/05/26 2.6. Reference 2.7. Recovery method NA 2.8. Remark DID/DTC LTM-161790 [Sign-off] VF7 NP LS build_LS#52_RLLV3FUV7TH766454 - VinFast TMS{}
[FPT][VF8 MKT][VN][FRS 7C.1.6E.2 V2] Widget on IPC disappears when TBT display | VN - Viet Nam | 2.1. Test Preconditions 1. Vehicle is ON 2. Gear P 3. Has internet 2.2. Test Steps 1. Switch Widget by MFS MENU -> Obser 2. Open VietMap -> Navigation to any destination 3. Press switch Widget by MFS MENU -> Obser 4. End Trip -> Press switch Widget by MFS MENU -> Obser 2.3. Expected Result 1&3&4 IPC display follow: ADAS prompt (if any) → Active call (if any) → Media → Turn-by-turn navigation → TPMS information → Weather → Return to ADAS prompt 2.4. Actual Result 1. OK 3. All Widget display TBT 3. All widget disappears 2.5. Exact time issue happens 14:28 15/05/26 2.6. Reference 2.7. Recovery method NA 2.8. Remark DID/DTC LTM-161790 [Sign-off] VF7 NP LS build_LS#52_RLLV3FUV7TH766454 - VinFast TMS{}
[Thermal AT&V_VF8NP_PTO ] The air outlet temperatures are not consistent. | VN - Viet Nam | [Pre-condition] Vehicle Model: VF8NP LHD VN ● Build vehicle : PTO ● VIN: RLLV3FUV7TH725483 ● Software Version: [^DID_RLLV3FUV7TH725483_VF8 NP_FRS 7C.1.6.0 TPV7_16-05-2026_15-21-02.xlsx] ● Test Standard : [^Thermal 001 AC Pull Down 2025 07 03 rev11.pdf] [Step] ● Perform soaking and testing according to the standard: [^Thermal 001 AC Pull Down 2025 07 03 rev11.pdf] [Expect] No issue observed during the test [Actual] The air outlet temperatures are not consistent. Report : [^VFVTV_Thermal_535_VF8NP PTO DVP AC cooldown 42 °C (1).pdf]
[VF8NP] [Water wading] VF8NP rear bumper damage in wading test | VN - Viet Nam | ● * What happened? ● Rear bumper damage, crack at bracket connect to under cover No water ingress inside cabin but rear bumper damage acceptable criteria: no part damage/no water ingress ● Why is it a problem? ● Part damaged in wading test ● When it happened? ● Wading test in 300mm depth of water with 15kph ● Who detected? ● VTnV Reliability ● Where detected? ● Wading track - HP plant ● How detected? ● Wading test in 300mm depth of water with 15kph, after wading check condition of underbody ● How many failure? 1 ride in this condition
[ePT]VF7(NP)_FRS 7C.1.6.0 V8_ Tow mode can not active when key in the car | VN - Viet Nam | Test Condition: 1. Vehicle in P Gear 2. LV battery voltage >= LV_VOLTAGE_NORM_TH 3. Key in the vehicle 4. Release brake pedal 5. User touch START button on MHU Expected Result: 1. CVC_ACTGear = P 2. UBatt>12 3. BCM_FL_Keyfob_Leftcar = No Alert 4. WCBS_BrkPedalSwSts = Unpressed 5. MHU_TowMode_Req = Active + CVC_Vehicle_Special_Mode = Tow mode + WCBS_TowMode_Feedback = Active + Change ActualGear to 2 "N" CVC_ACTGear = N Actual Result: With step 4: Tow mode can not active when key in the car Recovery: - Occurrences: Always
[VF8_NP] [7C.1.6.0v7] Strong jerk when LKA active | VN - Viet Nam | Precondition: ● Vehicle: RLLV3FUV4TH725487 ● FRS 7C.1.6.0v7 ● This issue occurs at around 17:43:20 ( 7:10:50 in canlog ) Procedure: 1. EV is moving on the road 2. EV depart lane and LKA active 3. Check behavior Expected result: 1. EV is moving on the road 2. EV depart lane and LKA active 3. No jerk occur Actual result: 1. OK 2. OK 3. NOK - Strong jerk when LKA active Attachment: ● Video: ● Can log: ● DID, MHU log, please check via ticket: VFM-597823
[FPT][VF8 MKT][VN][FRS 7C.1.6E.2 V3] The seatbelt warning is displayed incorrectly for the middle seat and the rear passenger seats. | VN - Viet Nam | 2.1. Test Preconditions 1. Vehicle is ON 2. Gear is P 2.2. Test Steps 1. Sit and fasten your seatbelts in the middle rear seat -> Obser 2. Sit and fasten your seatbelts in the back passenger seat -> Obser 2.3. Expected Result 1. Icon on central screen is green 2. Icon on central screen is green 2.4. Actual Result 1. Icon on central screen is red 1. Icon on central screen is red 2.5. Exact time issue happens Around 11:20 23/05/26 2.6. Reference 2.7. Recovery method NA 2.8. Remark The seatbelts for the middle seat and the rear passenger seat are being swapped.
[VF8_NP][7C.1.6.0v7]: MHU delays of displaying the driving mode change when driver rotating on the stalk | VN - Viet Nam | Precondition: ● Vehicle: RLLV3FUV4TH725487 ● FRS 7C.1.6.0v7 ● This issue occurs at around 20:40:44 ( around 05:25:01 on CANlog) Procedure: 1. Driver rotates on the stalk to change driving mode 2. Check MHU behavior Expected result: 1. Driving mode changed successfully 2. The MHU displays changes in driving mode Actual result: 1. OK 2. NOK – The MHU was slow to display the driving mode change until 20:42:00 Attachment: ● CAN log: ● Video: ● DID: ● CVC log, MHU log: please check via ticket: VFM-599023
[FRS 7C.1.6.0 TPV8] [VN] When LKA active LKA FCAM_LA_Popup = 3 but in can log the value is not update | VN - Viet Nam | Weather : Good Sunny VIN RLLV3FUV4TH725487 Preconditions: 1. SV ON 2. Auto Steer ON Test Steps: 1. Drive the SV at a speed above 50 km/h with the right/left. 2. Allow the SV to depart from the right/left solid or dashed lane line. 3. Check the LKA system behavior FCAM_LA_Popup during lane departure. Expected Result: 1. SV is driven above 50 km/h with the right/left turn. 2. SV departs from the right/left solid or dashed lane line. 3. LKA active and FCAM_LA_Popup = 3. Actual Result: 1. SV is driven above 50 km/h with the right/left turn. 2. SV departs from the right/left solid or dashed lane line. 3. LKA active and FCAM_LA_Popup = 0 (Value not update). Refer DTC DID MHU log in the ticket Refer DTC DID MHU in the ticket [IVF8NP-11701 [VF8 NP FRS 7C.1.6.0 TPV8] ELK and LKA Inoperative fault observed when AESA function...]
[VF8 NP FRS 7C.1.6.0 TPV8] FCAM_AEB_Target_Deceleration holds a positive value during the non active states | VN - Viet Nam | Precondition: Ignition/Engine ON Procedure: 1. Gear is D 2. TV placed in the center of the SV lane 3. Drive SV towards the TV at speed more than 10kmph Expected result: At Step 3: AEB get activated with deceleration request Other than AEB active state "FCAM_AEB_Target_Deceleration" signal should carry 0 Value. Actual result: At Step 3: AEB got activated with deceleration request Other than AEB active state "FCAM_AEB_Target_Deceleration" signal carry a positive Value "1.77m/s2". Req: State Explanation table SYS2_L2_AEBFCW-3048543
[VF8_NP] [7C.1.6.0TPV7] Vehicle Battery Range Lower Than Specified | VN - Viet Nam | Precondition: FRS: 7C.1.6.0v7 VIN number: RLLV3FUV4TH725487 Date:27/5/2026 *Procedure: * 1.Battery vehicle: 80% 2.Vehicle driving around Mac Thai To Street to Dinh Vu Roundabout. (about:141km) *Expected: * range test: >200km Actual result: Battery is reduce from 80%-<20% but only 141km Attachment: MHU log, DID, DTC, tbox, please check via:VFM-599257
[VF8_NP_VN] [7C.1.7.0TPV1] SVM: The front SVM camera sinks inward after a period of use. | VN - Viet Nam | Procedure: B1: Check the SVM cameras. Expect: The cameras are securely mounted and not recessed inward. Actual: The front SVM camera sinks inward after a period of use. As a result, the SVM feature cannot be calibrated at the EOL station. Ticket same: IVF8NP-3851 [VF7-PTO] - Check front bracket camera - VinFast TMS
[In-Region][FRS 7C.1.6.0 V7][VF8 NP][EEU] Duplicate UI of Car Buddy on MHU and IPC | VN - Viet Nam | Pre-condition: 1. HV ON 2. FRS 7C.1.6.0 V7 3. Make sure MHU and IPC in good condition Test produce: 1. Observed Car buddy on MHU and IPC Actual: ● Duplicate UI show the status of vehicle on MHU and IPC ● Proposal: ● Design UI on MHU is full screen > Only service for infotainment ● Keep UI the vehicle status on IPC is enough for driver. Benchmark competitor: UI competitor: + AION UT: + Wuling Cloud:
[EE‑FOTA_VF8NP_VN_FRS 7C.1.7.0 TPV1] Fota install success, vehicle lost HV | VN - Viet Nam | Test steps: Press install on MHU Expected: Campaign Install Succeeded no error, vehicle working normal Actual: Campaign Install Succeeded, hit the break vehicle lost HV Time issue happen: 29/May/26, 20h45-20h50 Detail Occurrence: 1/1/1 Recover actions: NA¦
[VF8_NP] [8E.1.7.0 TPV1] LKA: LKA is abnormally fault status when vehicle is moving | VN - Viet Nam | Procedure: B1: Vehicle is moving B2: Check signals Expect: LKA isn't abnormally fault status when vehicle is moving Actual: LKA is abnormally fault status when vehicle is moving DID: LTM-165283 MHU + VIDEO + CVC Log: EMT-218076 01/06/2026 LOG - VinFast TMS CAN: IVF8NP-13252
[VF8_NP] [8E.1.7.0 TPV1] ELK: ELK is abnormally fault status when vehicle is moving | VN - Viet Nam | Procedure: B1: Vehicle is moving B2: Check signals Expect: ELK isn't abnormally fault status when vehicle is moving Actual: ELK is abnormally fault status when vehicle is moving Time CAN LOG: As picture DID: LTM-165283 MHU + VIDEO + CVC Log: EMT-218076 01/06/2026 LOG - VinFast TMS CAN: IVF8NP-13252